## Project plan
Epic | April 20 - 24 | April 27 - May 1 | May 4 - May 8 | May 11 - May 15 | May 18 - May 22 | May 25 - May 29
Platform & Foundations
Conversational UI
Financial Planning
Demo preparation
Deliverables/Milestones | Azure services provisioned | Full stack flow running in Azure Data sources updated | Workflows 1 and 2 implemented Financial Planning requirements finalized | Multi-agent factory set up Workflows 3 and 4 implemented Financial Planning backend set up | Financial Planning view completed Conversational UI with Intents set up | Demo and communications material updated
Provision core services and accesses
Create git repo and branching strategy
Backend scaffolding (config, api layer, runtime)
Consolidate and update source data
Multi-agent factory setup
Fabricate new data
Workflow 1 build - Client Review & Prep
Workflow 2 build - Portfolio & Performance
Workflow 3 build - Meeting Strategy & NBA
Workflow 4 build - Client Sentiment
Define features & functionality
Fabricate data needed
Design & Build Workflows
Enable Intent selection
Multi-agent factory UI build
Go over and update remaining placeholders
Update and refine talk-tracks
Dry runs, internal demo sessions
Communications build
Tool repository/MCP server set-up

## Prioritized workflows
Conversational UI
Workflow | Description | Example questions supported | Complexity | Data needed | Data source | Data availability | Data fabrication needed?
Client Review & Prep | Queries regarding client information, comparison of client goals or events or information about past interactions | Questions about client information (Major life events, goals, household info) | Easy | Client info table | SQL | All data available
|  | Summarization of last X advisor notes for Family Y | Medium | Call transcripts, email history, advisor notes | VectorDB | Need advisor notes table | Yes, generate advisor notes
|  | Comparison across multiple clients (goals, recent convos, docs on file, upcoming action items) | Hard | Client info table,Call transcripts, email history, advisor notes | SQL, Vector DB | Need advisor notes table | Yes, generate advisor notes
Portfolio & Performance | Queries regarding client portfolio composition, comparison of performance across clients | Questions on their portfolio and assets | Easy | Portfolio data | SQL | All data available
|  | Summarize and compare performance for the top X clients | Medium | Portfolio data | SQL | All data available
|  | Highlight clients with positions at risk given recent market events | Hard | Portfolio data, Market events | SQL, Web search | Need web search data source | Yes, generate advisor notes
Meeting Strategy & Next Best Action | Queries supporting meeting and interaction preparation, sucha s agenda creation, listing of action items and quesitons to prepare | Create agenda for next meeting with family X | Easy | Call transcripts, email history, advisor notes | VectorDB | Need advisor notes table | Yes, generate advisor notes
|  | List most important actions for the top X households | Medium | Call transcripts, email history, advisor notes | VectorDB | Need advisor notes table | Yes, generate advisor notes
|  | Questions to ask to uncover unmet needs or planning risk | Hard | Call transcripts, email history, advisor notes | VectorDB | Need advisor notes table | Yes, generate advisor notes
Client Sentiment & Communication Intelligence | Uncovering client concerns, sentiment and communication themes | Recent sentiment/concern/uncertainty expressed from clients | Easy | Call transcripts, email history, advisor notes | VectorDB | Need advisor notes table | Yes, generate advisor notes
|  | What themes are emerging across recent multiple client conversations X weeks? | Medium | Call transcripts, email history, advisor notes | VectorDB | Need advisor notes table | Yes, generate advisor notes
|  | Which clients require extra attention given raised concerns given current market conditions? | Hard | Call transcripts, email history, advisor notes, market events | VectorDB, Web search | Need advisor notes table and web search data source | Yes, generate advisor notes
AI Feature list
The four workflows proposed will enable implemetation of additional AI features on the UI. The flows can be run as a batch process as data is being updated and do not need to be run every time the UI is launched. While this is alower priority than the convserational UI capabilities, the following AI features are expected to be in scope for the main dashboard page
Quick action tiles
Clients requiring attention tiles
Upcoming meetings
Tasks & Follow-up
Agent Factory
Multi-agent actory will support fast roll-out of new agents for any workflow modifications or additions. Preliminary list of agents include:
Agent | Primary purpose | Key capabilities | Key data inputs | Typical outputs | Workflows supported | Dependencies | Notes
Orchestrator / Intent Router | Route advisor asks to the right workflow | Intent classification; tool selection; multi-agent planning | Conversation + workflow catalog + client/advisor context | Execution plan + sub-agent calls | All | All other agents | Keeps responses consistent and compliant
Client Info Retrieval Agent | Fetch client/household facts quickly | NL→SQL query generation; joins across client entities | ClientDetails, AdvisorClient, CRM activities, Financial planning facts | Structured client snapshot (goals, household, life events) | Client Review & Prep; Meeting Strategy | SQL access + schema | Foundation for almost every workflow
Interaction Summarizer Agent | Summarize recent communications and notes | Vector retrieval; summarization; timeline generation | Call transcripts, advisor notes, Email/EmailReply | Last X interactions summary + follow-ups | Client Review & Prep; Meeting Strategy; Sentiment | VectorDB + chunking/indexing | Critical when ‘advisor notes table’ is missing
Meeting Prep & Agenda Agent | Create meeting briefs and agendas | Agenda drafting; highlights; open items; questions to ask | Calendar/CRM meetings, tasks, Client 360, Interaction summaries | 1‑pager prep + agenda + action checklist | Meeting Strategy & Next Best Action | Client 360 + Summarizer | Directly improves meeting quality and efficiency
Document & Compliance Agent | Track required/stale documents and compliance flags | Document classification; gap detection; policy checks | Box files, ComplianceHub, CRM tasks/requests | Missing docs list + compliance alerts | Client Review & Prep | Document store connectors | Helps avoid last‑minute scrambles and audit issues
Portfolio Analytics Agent | Analyze holdings, exposure and risk | Concentration analysis; sector/style exposure; risk metrics | PortfolioData/holdings, account balances | Risk/exposure summary + at‑risk positions | Portfolio & Performance | Market Intel (optional) | Pairs well with Market Intelligence Agent
Performance & Benchmark Agent | Explain performance relative to benchmarks | Return calculations; benchmark comparisons; attribution narrative | PortfolioData, policy benchmark data, Dynasty investment knowledge | Under/over‑performance flags + talking points | Portfolio & Performance | Benchmark mapping | Supports proactive outreach and review prioritization
Market Intelligence Agent | Connect portfolios to current market events | News/event retrieval; summarization; impact tagging | MarketHighlights + web search | Market brief + client impact candidates | Portfolio & Performance; Sentiment | Web search data source | Useful for ‘what’s changed since last meeting’
Sentiment & Theme Mining Agent | Detect concerns and themes across clients | Sentiment classification; topic clustering; trend detection | EmailInsight, call transcripts, advisor notes | Theme dashboard + clients needing attention | Client Sentiment & Communication Intelligence | VectorDB + sentiment model | Improves retention and timely reassurance
Next Best Action (NBA) Agent | Prioritize actions across households | Opportunity scoring; urgency/impact ranking; task generation | NextBestAction, CRM tasks, client segments, sentiment | Ranked action list + rationale | Meeting Strategy & Next Best Action | Scoring heuristics/metrics | Turns insights into an actionable daily plan
Planning Gap / Financial Planning Agent | Identify missing planning work and triggers | Rules + scenario prompts (RMD, Roth, estate, insurance) | Financial planning facts, age, account types, goals, documents | Planning recommendations + questions to ask | Client Review & Prep; Meeting Strategy | Planning rule library | Great for uncovering unmet needs and risk

## Question list
In-scope workflows
Good to have workflows
Out of scope workflows
Question category | Question # | Value | Indicated data sources | Intent | Priority | Data available? | Questions | Comments | Data source 1 | Data source 2 | Data source 3 | Data source 4 | Data source 5 | Data source 6 | Why is this question relevant? (Copilot)
Client Review & Prep | 1 | Which clients have had a major life event recently but no updated financial plan or scheduled review meeting? | CRM activities [notes/emails mentioning life events] + financial planning facts [stale plan dates] + CRM activities [meeting calendar gaps] + contact profiles + transaction activity) |  |  | Yes | What qualifies as 'Major' life events? Is there a column for financial plan? | Output need to be a list | Email | EmailReply | EmailInsight | ClientDetails | PortfolioData |  | Flags clients with meaningful life changes who may now be off-plan, letting the advisor proactively schedule a review, update assumptions, and prevent service/retention risk.
Client Review & Prep | 2 | Which clients over 50 have estate planning documents that are more than 3 years old and have had significant balance growth or life changes since then? | Box files [estate plan dates] + account balances [growth trajectory] + CRM activities [life event mentions] + contact profiles [age, family changes] + transaction activity) | [11 empty] | Estate documents often become stale as families and assets change; this pinpoints clients who may face avoidable tax/legal issues and need an updated estate review.
Client Review & Prep | 3 | Compare my top ten clients — their goals, recent conversations, portfolio positioning, documents on file, and any upcoming action items — so I can identify service gaps. | Contact profiles + CRM activities + financial planning facts + holdings + account balances + transaction activity + billing data + Box files + Dynasty Investment knowledge) | [11 empty] | A side-by-side view of top clients exposes service gaps, missed follow-ups, and cross‑planning opportunities so the advisor can deliver consistent high‑touch service.
Client Review & Prep | 4 | Give me a one‑page prep for my meetings this week: key clients, large transactions since last review, open tasks, and recent interactions. | CRM activities + account balances + transaction activity + contact profiles) | [11 empty] | Concise meeting prep reduces surprises and improves meeting quality by surfacing transactions, tasks, and context that should drive the conversation.
Client Review & Prep | 5 | Summarize the last three advisor notes for the Smith household and any pending follow‑ups. | CRM activities [notes, tasks]) | Clients |  |  | Do we only need a working answer for the Smith household or any household? | [7 empty] | Summarizing recent notes ensures continuity and accountability so commitments aren’t dropped and the next client interaction picks up where the last left off.
Client Review & Prep | 6 | Which clients have incomplete or missing documents ahead of scheduled meetings? | Box files + CRM activities [scheduled meetings] + contact profiles) | [11 empty] | Missing documents can derail a meeting and create compliance issues; identifying gaps early enables timely requests and smoother, more productive reviews.
Client Review & Prep | 7 | Which clients haven't I received updated tax documents for yet?" | Box files [tax documents] + contact profiles + CRM activities [requests/follow-ups]) | [11 empty] | Tax documents drive planning decisions; knowing what’s missing helps the advisor follow up, avoid filing surprises, and time-sensitive tax moves.
Portfolio & Performance | 8 | Which clients hold concentrated positions or sectors that are at risk given current market news, and when did I last discuss their risk tolerance or investment strategy with them? | Holdings [concentration analysis] + web search [current market/sector risks] + Dynasty Investment knowledge [model commentary] + CRM activities [last strategy conversation] + financial planning facts [risk tolerance]) |  |  |  | Is web search in scope? | [7 empty] | Connects portfolio risk to current market drivers and suitability history so the advisor can address concentrations, confirm risk tolerance, and document strategy conversations.
Portfolio & Performance | 9 | Which households underperformed their policy benchmark by more than 150 bps in the last quarter? | Holdings + account balances + Dynasty Investment knowledge [benchmarks/commentary]) | [11 empty] | Material underperformance requires explanation and potential action; this helps the advisor prioritize reviews, communicate drivers, and adjust allocations if warranted.
Portfolio & Performance | 10 | List accounts with outsized single‑security concentration risk above the firm threshold. | Holdings + account balances + billing data [account type/attributes]) | [11 empty] | Highlights accounts breaching concentration policies so the advisor can reduce single‑name risk, align with firm guidelines, and protect client outcomes.
Portfolio & Performance | 11 | Show clients with realized or unrealized losses suitable for tax‑loss harvesting this month. | Holdings + transaction activity [realized gains/losses] + account balances) | [11 empty] | Identifies tax‑loss harvesting opportunities to offset gains, reduce current tax liability, and add measurable value through tax‑aware portfolio management.
Portfolio & Performance | 12 | For my top 20 households, summarize performance attribution and biggest drivers of variance. | Holdings + account balances + transaction activity + Dynasty Investment knowledge [commentary/trade rationale]) |  |  |  | Top 20 in what way? Total assets? | [7 empty] | Attribution explains the “why” behind results; it equips the advisor to communicate performance drivers clearly and make evidence-based adjustments.
Cash & Liquidity | 13 | Which clients have large cash positions sitting uninvested with no note explaining why, and what has our recent investment commentary said about deploying cash in the current market environment? | Holdings [cash allocations] + account balances + transaction activity [recent inflows with no subsequent buys] + CRM activities [notes] + Dynasty Investment knowledge [market outlook/trade rationale] + web search [current conditions]) | [11 empty] | Large idle cash can be costly; this finds deployable cash and ties it to market commentary so the advisor can recommend an appropriate strategy and document rationale.
Opportunities & Growth | 14 | Identify households with upcoming RMDs and indicate funding options from available cash or distributions. | Account data [account type/attributes] + holdings + contact profiles [age/DOB] + transaction activity + financial planning facts) |  |  |  | RMD = Required Minimum Distribution? | [7 empty] | RMDs have strict deadlines and penalties; surfacing upcoming RMDs and funding sources supports tax-efficient withdrawals and smoother cash-flow planning.
Opportunities & Growth | 15 | Which non‑managed accounts over $100,000 have investable assets, are not annuities, and I have not talked to the client about managing those assets in over 2 years? | Account data [attributes, type, custodian] + account balances + CRM activities [notes/meetings]) | [11 empty] | Non‑managed assets are a wallet‑share opportunity; this finds sizable accounts with no recent discussion so the advisor can re-engage and propose management.
Opportunities & Growth | 16 | Which prospects in my pipeline have a similar profile to my top 10 clients by revenue, and what talking points would be most relevant for outreach? | Contact profiles [prospect demographics] + billing data [top revenue clients] + holdings + Dynasty Investment knowledge [relevant commentary] + web search [prospect company/industry news]) | [11 empty] | Pattern-matching to top clients helps prospecting efficiency by prioritizing similar high-value prospects and tailoring outreach with relevant, timely talking points.
Opportunities & Growth | 17 | Which clients have referred new prospects in the last 90 days, and what is the follow‑up status? | CRM activities [notes, tasks, emails] + contact profiles) | [11 empty] | Referrals are high-conversion leads; tracking them and follow-up status ensures prompt acknowledgment, better pipeline hygiene, and higher close rates.
Opportunities & Growth | 18 | Identify households nearing key liquidity events (vesting, business sale, inheritance) from CRM notes. | CRM activities [notes/emails] + contact profiles + financial planning facts + web search [employer/company news]) | [11 empty] | Liquidity events create major planning moments; detecting them early enables proactive tax, investment, and cash-management planning and strengthens relationships.
Tax & Planning | 19 | Which clients have financial plan assumptions that are now materially out of line with their actual income, expenses, or portfolio performance? | Financial planning facts [projected assumptions] + account balances + transaction activity [actual deposits/withdrawals as income/expense proxies] + holdings [actual returns vs. assumed returns]) | [11 empty] | Plans are only useful when assumptions match reality; this pinpoints drift so the advisor can recalibrate projections, prevent shortfalls, and keep advice credible.
Tax & Planning | 20 | List clients with concentrated low‑basis positions and propose tax‑aware diversification paths. | Holdings [cost basis, concentration] + transaction activity + Dynasty Investment knowledge [model commentary] + web search [current market conditions]) | [11 empty] | Low-basis concentration creates both risk and tax friction; this helps the advisor design tax-aware diversification paths and discuss tradeoffs with the client.
Tax & Planning | 21 | Who is approaching net investment income tax thresholds and may benefit from planning? | Financial planning facts [income/projections] + holdings + transaction activity [distributions/gains] + account balances) | [11 empty] | Approaching NIIT thresholds can trigger extra tax; identifying clients near the cutoff enables proactive income/gain management and tax-efficient strategies.
Tax & Planning | 22 | Identify households with upcoming college funding needs and current 529 contributions vs. goal. | Financial planning facts [goals, assumptions] + account balances + transaction activity [contributions] + contact profiles [dependents/ages]) | [11 empty] | College funding is time-bound; comparing contributions to goals helps the advisor keep families on track and adjust savings/investment plans early.
Alerts & Monitoring | 23 | Which clients haven't heard from me in over 3 months, have more than $1M in assets, and have had something notable happen — in their portfolio, their plan, or in the news about their employer or industry? | CRM activities [last contact date] + account balances [AUM filter] + transaction activity [unusual patterns] + financial planning facts [goal progress] + contact profiles [employer] + web search [employer/industry news]) | [11 empty] | High-value clients expect proactive service; this surfaces those overdue for contact plus new developments so the advisor can reach out before issues escalate.
Alerts & Monitoring | 24 | Which clients had withdrawals or outbound transfers in the last 90 days that I wasn't aware of, and is there any context in our notes or emails about why? | Transaction activity [withdrawals/transfers] + CRM activities [emails/notes for context] + account balances [impact assessment] + CRM activities [tasks/follow-up status]) | [11 empty] | Unexplained withdrawals can signal dissatisfaction or a life change; this helps the advisor investigate quickly, document context, and reduce attrition risk.
Alerts & Monitoring | 25 | Which accounts over $100,000 that weren't recently funded in the last six months have an effective advisory fee rate that is 10% or more different relative to the IMA fee rate? | Billing data + account balances + transaction activity + Box files [IMA]) | [11 empty] | Fee inconsistencies can create compliance and reputational risk; this detects anomalies so the advisor can correct billing, explain differences, and protect revenue.
Alerts & Monitoring | 26 | Surface notable changes for my book in the last 24 hours: large deposits/withdrawals, performance outliers, or risk flags. | Transaction activity + account balances + holdings + CRM activities) | [11 empty] | Near-real-time alerts let the advisor respond quickly to meaningful client changes, improving service responsiveness and reducing risk from missed signals.
Alerts & Monitoring | 27 | Notify me if a household's fee breakpoints or billing anomalies are triggered. | Billing data + account balances + transaction activity) | [11 empty] | Breakpoint and billing anomaly monitoring prevents over/underbilling, supports transparent client communication, and reduces operational and regulatory risk.
Relationship & Household Intelligence | 28 | Which households have multiple decision-makers or family members involved, and who should be included in the next conversation? | Contact profiles [household relationships, roles] + CRM activities [meeting attendees, notes] + financial planning facts [shared goals]) | [11 empty] | Knowing who makes decisions avoids missed stakeholders; it improves meeting attendance, aligns communications, and increases the likelihood of implementation.
Relationship & Household Intelligence | 29 | Show me households where one spouse or family member is highly engaged and the other is disengaged. | CRM activities [emails, meeting attendance, portal activity] + contact profiles [household members]) | [11 empty] | Engagement imbalance can hide dissatisfaction; this helps the advisor adjust communication styles, involve the right people, and protect the relationship.
Relationship & Household Intelligence | 30 | Which clients have aging parents, adult children, or grandchildren that create planning needs I have not addressed recently? | Contact profiles [family relationships, ages] + CRM activities [notes] + financial planning facts [goals]) | [11 empty] | Extended-family dynamics drive new needs (caregiving, gifting, education, estate); this highlights planning topics that may require proactive outreach.
Relationship & Household Intelligence | 31 | Which households have next-generation family members who are not yet connected to me? | Contact profiles [family tree] + CRM activities [interaction history] + CRM activities [meeting participants]) | [11 empty] | Next-gen engagement supports multi-generational retention; this identifies relationship gaps so the advisor can connect early and reduce future asset leakage.
Relationship & Household Intelligence | 32 | Summarize the full household dynamic for this client — key decision-makers, beneficiaries, business ties, trusts, and recent family developments. | Contact profiles + CRM activities + Box files + financial planning facts) | [11 empty] | A household “map” enables holistic planning and better coordination across entities, trusts, and beneficiaries—reducing blind spots and improving advice quality.
Meeting Strategy & Next Best Action | 33 | For each meeting on my calendar this week, what are the top three issues I should address and the most relevant follow-up action? | CRM activities + transaction activity + account balances + financial planning facts + Box files) | [11 empty] | Meeting-specific priorities and follow-ups improve outcomes by focusing on the highest-impact issues and ensuring action items are captured and executed.
Meeting Strategy & Next Best Action | 34 | What has changed for this household since our last review that should shape today’s conversation? | CRM activities + transaction activity + account balances + holdings + financial planning facts + Box files) | [11 empty] | Surfacing what changed since the last review keeps the discussion relevant, supports timely plan updates, and demonstrates proactive stewardship.
Meeting Strategy & Next Best Action | 35 | Draft the best agenda for my next review with the Johnson family based on open planning issues, portfolio changes, and recent conversations. | CRM activities + holdings + financial planning facts + transaction activity + open tasks) | [11 empty] | A tailored agenda raises meeting efficiency and client confidence by organizing discussion around current issues, portfolio changes, and pending planning gaps.
Meeting Strategy & Next Best Action | 36 | What questions should I ask this client to uncover unmet needs or planning risks? | Contact profiles + CRM activities + financial planning facts + holdings + Box files) | [11 empty] | Discovery questions reveal unmet needs and risks; this helps the advisor expand planning scope, personalize advice, and uncover actionable next steps.
Meeting Strategy & Next Best Action | 37 | What is the most important thing I should do next for each of my top 25 households? | CRM activities + financial planning facts + holdings + account balances + open tasks + contact profiles) | [11 empty] | Advisors need prioritization across many households; this identifies the highest-leverage next actions to maximize client outcomes and time efficiency.
Retention Risk & Service Gaps | 38 | Which high-value clients show signs of disengagement or attrition risk? | CRM activities [declining responsiveness, missed meetings] + account balances + transaction activity [outflows] + contact profiles + sentiment from notes/emails) | [11 empty] | Early disengagement signals allow proactive retention; this helps the advisor intervene with service recovery and protect high-value relationships.
Retention Risk & Service Gaps | 39 | Which clients have reduced wallet share, outbound transfers, or fewer interactions over the last 12 months? | Account balances + transaction activity + CRM activities + billing data) | [11 empty] | Wallet-share decline and transfers indicate leakage; this helps the advisor diagnose causes, re-engage clients, and address competitive threats.
Retention Risk & Service Gaps | 40 | Which top households are receiving below-target service relative to their revenue or complexity? | Billing data + CRM activities [meeting frequency, tasks] + contact profiles [complexity] + financial planning facts) | [11 empty] | Service levels should match revenue and complexity; this flags misalignment so the advisor can rebalance effort, adjust segmentation, or add resources.
Retention Risk & Service Gaps | 41 | Which clients may feel neglected because they have unresolved requests, stale plans, or delayed follow-ups? | CRM activities [open tasks, response lag] + financial planning facts [stale plan date] + Box files [missing docs]) | [11 empty] | Unresolved requests and stale plans erode trust; this identifies service failures early so the advisor can close loops and reduce attrition risk.
Retention Risk & Service Gaps | 42 | Rank my book by retention risk and explain why each household is flagged. | CRM activities + transaction activity + account balances + billing data + contact profiles) | [11 empty] | A ranked retention-risk view turns signals into a plan—helping the advisor focus outreach, prioritize remediation, and track why clients are at risk.
Planning Expansion Opportunities | 43 | Which clients appear to need estate, tax, insurance, or trust planning that we have not formally addressed? | CRM activities + Box files + financial planning facts + contact profiles + holdings) | [11 empty] | Clients often need planning beyond investments; this surfaces estate/tax/insurance/trust gaps so the advisor can broaden value and reduce future issues.
Planning Expansion Opportunities | 44 | Which households have enough complexity that they may benefit from a family office-style service model? | Account balances + contact profiles [entities, trusts, beneficiaries] + Box files + CRM activities) | [11 empty] | High complexity can require deeper coordination; this identifies households that may benefit from a higher service tier and more comprehensive solutions.
Planning Expansion Opportunities | 45 | Which clients likely need a review of beneficiary designations, trust structure, or account titling? | Box files [trust/estate docs] + account attributes + contact profiles + CRM activities) | [11 empty] | Beneficiaries and titling drive estate outcomes; this helps prevent costly mistakes, supports compliance, and ensures documents match client intent.
Planning Expansion Opportunities | 46 | Which business-owner clients may need succession, liquidity, or key-person planning? | Contact profiles [business ownership] + CRM activities [notes] + Box files + web search [business/company developments]) | [11 empty] | Business owners face unique risks and opportunities; this flags succession and key-person needs so the advisor can protect enterprise value and family wealth.
Planning Expansion Opportunities | 47 | Which clients have insurance coverage on file that appears outdated relative to their current balance sheet or family circumstances? | Box files [insurance docs] + account balances + contact profiles + CRM activities) | [11 empty] | Outdated insurance can leave families exposed; this identifies coverage gaps relative to today’s balance sheet and life changes, prompting a review.
Tax-Smart Advisor Questions | 48 | Which clients are likely to have capital gains exposure this year based on realized activity and current embedded gains? | Transaction activity + holdings [cost basis] + account balances + financial planning facts) | [11 empty] | Capital gains exposure affects tax bills and cash needs; knowing likely gains enables proactive tax planning, withholding/estimated tax adjustments, and strategy timing.
Tax-Smart Advisor Questions | 49 | Which households may benefit from charitable giving strategies such as DAF funding or appreciated securities gifts? | Holdings [appreciated positions] + financial planning facts [charitable goals] + CRM activities + account balances) | [11 empty] | Charitable strategies can improve tax efficiency and client satisfaction; this helps align giving intent with the best vehicles (DAF, appreciated gifts, etc.).
Tax-Smart Advisor Questions | 50 | Which clients may be candidates for Roth conversion analysis this year based on income expectations and account mix? | Financial planning facts [income/projections] + holdings [IRA types] + contact profiles [age] + account balances) | [11 empty] | Roth conversions can reduce lifetime taxes and future RMDs; identifying candidates helps the advisor prioritize analyses during optimal tax windows.
Tax-Smart Advisor Questions | 51 | Which clients have uneven income or liquidity patterns that may warrant estimated tax planning or withholding review? | Transaction activity + financial planning facts + account balances + CRM activities) | [11 empty] | Irregular income/cash flow increases underpayment risk; this supports estimated tax and withholding planning to avoid penalties and surprises.
Tax-Smart Advisor Questions | 52 | Which clients have large charitable intent, low-basis assets, and no documented tax strategy discussion? | Holdings + financial planning facts + CRM activities + Box files) | [11 empty] | When charitable intent and low-basis assets exist, a documented strategy is valuable; this prompts timely, tax-smart giving conversations and documentation.
Business Owner / Executive Client Intelligence | 53 | Which clients are executives or business owners with concentrated employer stock, vesting schedules, or liquidity event exposure? | Contact profiles [employment/business role] + holdings + transaction activity + CRM activities + financial planning facts) | [11 empty] | Executives often have concentrated employer risk and complex comp; this helps the advisor manage concentration, plan vesting, and prepare for liquidity events.
Business Owner / Executive Client Intelligence | 54 | Which households may have upcoming planning needs tied to company events like IPOs, mergers, layoffs, or bonus cycles? | Contact profiles [employer/company] + CRM activities + web search [company news]) | [11 empty] | Company events can rapidly change client finances; spotting them supports proactive planning around benefits, layoffs, IPO windows, and compensation changes.
Business Owner / Executive Client Intelligence | 55 | Show me clients whose business value or compensation structure may have changed materially since their last plan. | Contact profiles + CRM activities + financial planning facts + web search) | [11 empty] | Material changes in business value or comp can invalidate a plan; this signals when to refresh projections, funding strategies, and risk management.
Business Owner / Executive Client Intelligence | 56 | Which business-owner households should I proactively contact about succession, buy-sell funding, or exit planning? | Contact profiles + Box files + CRM activities + financial planning facts) | [11 empty] | Succession and exit planning are long-lead items; identifying who to contact early improves outcomes, reduces business disruption risk, and deepens relationships.
Client Sentiment & Communication Intelligence | 57 | Which clients have expressed concern, uncertainty, or frustration recently in notes or emails? | CRM activities [email text, notes, call summaries]) | [11 empty] | Negative sentiment is a leading indicator of churn; surfacing it helps the advisor address concerns quickly with empathy and corrective actions.
Client Sentiment & Communication Intelligence | 58 | Which households are asking more questions than usual about markets, taxes, or cash needs? | CRM activities [emails, notes, call summaries] + chat/portal interactions if available) | [11 empty] | A spike in questions often signals anxiety or changing needs; this helps the advisor prioritize education and outreach before concerns become attrition.
Client Sentiment & Communication Intelligence | 59 | What themes are emerging across my book from recent client conversations? | CRM activities [notes, call summaries, emails] + client interaction logs) | [11 empty] | Theme detection across the book informs proactive communications, meeting agendas, and campaigns—helping the advisor stay relevant and anticipate needs.
Client Sentiment & Communication Intelligence | 60 | Which clients may need proactive reassurance given recent market volatility and their past behavior? | Financial planning facts [risk tolerance] + CRM activities [prior reactions] + holdings + web search [market conditions]) | [11 empty] | Volatility triggers behavioral mistakes; this identifies clients likely to need reassurance and coaching based on past reactions and current conditions.
Client Sentiment & Communication Intelligence | 61 | Summarize this client’s current sentiment, top concerns, and likely objections before I call them. | CRM activities + financial planning facts + holdings + recent interactions) | [11 empty] | Pre-call sentiment and objections improve communication quality; the advisor can tailor messaging, reduce friction, and increase follow-through.
Workflow & Productivity | 62 | Which follow-ups assigned to me are overdue, and which matter most based on client value or urgency? | CRM activities [tasks] + billing data + account balances + contact profiles) | [11 empty] | Overdue follow-ups create service and compliance risk; prioritizing by client value/urgency helps the advisor focus on what matters most.
Workflow & Productivity | 63 | Where am I spending time on low-value service work that could be automated or delegated? | CRM activities [task categories, time stamps] + service logs) | [11 empty] | Understanding low-value time sinks enables better delegation/automation, improving advisor capacity for high-impact client work.
Workflow & Productivity | 64 | What are the top unresolved issues across my book right now? | CRM activities [tasks, notes] + Box files [missing docs] + financial planning facts + transaction activity) | [11 empty] | A consolidated view of unresolved issues helps the advisor plan remediation, prevent escalation, and improve overall service delivery.
Workflow & Productivity | 65 | Prepare outreach drafts for the five highest-priority clients I should contact today. | CRM activities + contact profiles + holdings + account balances + financial planning facts) |  |  |  | How are high-priority clients determined? | [7 empty] | Draft outreach saves time and standardizes quality; focusing on top priorities increases engagement and accelerates completion of key actions.
Workflow & Productivity | 66 | Which households need attention this week, ranked by urgency, complexity, and revenue impact? | CRM activities + account balances + billing data + financial planning facts + transaction activity) | [11 empty] | Ranking households by urgency, complexity, and revenue impact helps the advisor allocate time intentionally and reduce the chance of missing critical work.
Compliance / Documentation / Operational Quality | 67 | Which client households have recommendations in notes but no documented rationale or follow-up? | CRM activities [notes, tasks] + compliance records if available) | [11 empty] | Recommendations without rationale/follow-up create regulatory and liability risk; this supports documentation, supervision, and closing the loop with clients.
Compliance / Documentation / Operational Quality | 68 | Which accounts are missing required documents, signatures, or recent suitability updates? | Box files + account data + financial planning facts + CRM activities) | [11 empty] | Missing documents/signatures/suitability updates can trigger compliance findings; this helps maintain regulatory readiness and operational accuracy.
Compliance / Documentation / Operational Quality | 69 | Which recent client interactions should have triggered a plan update, compliance note, or task but did not? | CRM activities + financial planning facts + workflow rules) | [11 empty] | If triggers are missed, risks compound; this highlights process gaps so the advisor can create tasks/notes, update plans, and improve workflows.
Compliance / Documentation / Operational Quality | 70 | Which clients have stale beneficiary, risk tolerance, or IPS information on file? | Box files + financial planning facts + account attributes + CRM activities) | [11 empty] | Stale beneficiary, risk tolerance, or IPS data can make advice unsuitable; this ensures records are current and recommendations remain aligned with client goals.

## Summary
Utility / Infra | Meaning (Pure Agentic)
Memory | Persistent episodic and semantic storage for conversations, decisions, and outcomes. Replaces workflow/task state.
Streaming | Real-time LLM token streaming to the UI (SSE/WebSocket).
UI Triggers | Frontend buttons or actions that bias agent intent without enforcing workflows.
Token Parser | Deterministic extraction of structured tokens (OPPORTUNITY, PLAN_ITEM, CARD).
Context Injection | Structured client, meeting, and plan data injected into prompts.
Curated Content | Human-approved static/semi-static content (nudges, research, presets).
Export | Formatting AI output into Word, PDF, or email artifacts.
Deterministic Compute | Non-AI calculations (scenarios, projections, math).
Prompt Shaping | Dynamic construction of system prompts based on mode and role.
Metrics Engine | Calculation of opportunity signals and KPIs.
Value Calculator | Formula-based prospect revenue estimation.
Search Index | Indexed datasets for fast retrieval (e.g., Azure AI Search).
Heuristics | Simple non-AI rules that surface signals.
Web Speech API | Browser-native speech recognition and synthesis.
Execution Hooks | Integration points for real-world actions (suggested, not enforced).
LLM Router | Runtime selection between primary and fallback LLMs.
Failover Logic | Retry and fallback handling for LLM or service failures.
SSE | Server-Sent Events transport for streaming.
Prompt Builder | Central service assembling system prompts, constraints, and context.

## Data Inventory
Table summaries
Table name | Data entity | Table description | Status | Supports feature (AEON 1.0)
AIGrounInsight | Client | Call and client summaries and categorization of call, goals and wealth topics | Used | AI Group Insights Modal: opened via "AI Group Insights" button above the Previous Calls table; shows cross-call aggregated insights, client summary, smart insights, and communication timeline.
AdvisorClient | Client + Advisor | Client-advisor mapping, client type and total asset amount | Used | My Clients card on the landing dashboard: sortable client list showing name, AUM, wallet share, segment; click-through to individual client 360 view.
AdvisorCoaching | Advisor | ??? | Used | Advisor Coaching card on the landing dashboard: available coaching credits, training modules list, completion progress.
AdvisorDetails | Advisor | Description of advisors, # accounts etc | Used | My Dashboard top bar: advisor profile picture, name, date display; navigation dropdown; dashboard summary cards (# of accounts, tasks, peer ranking, open opportunities). Client Onboarding form
AdvisorPerformance | Advisor | Description of advisor performance (revenue, growth) | Used | My Performance card on the landing dashboard: AUM total, revenue breakdown, client segment distribution chart. Also supplies AUM total to the Portfolio Simulator.
chat_memory | System | Past queries and responses log, agents used | Used | No UI. Backend-only evaluation logging; write call is commented out.
ClientDetails | Client + Advisor | Details about clients, name, goals, marital status, household, sentiment, status etc | Used | Client 360 View → Client Profile panel: personal info, contact details, relationship manager, risk profile, life events, household members. Also feeds the Ask Aeon copilot sidebar and standalone copilot Q&A page for NL→SQL queries. Client Onboarding form page
CollaborationHub | Advisor | Summary of which clients each advisor has | Used | Collaboration Hub card on the landing dashboard: advisor network contacts, team members, collaboration activity feed.
ComplianceHub | Client | List of clients and their next compliance-related recommendation | Used | Risk & Compliance Hub card on the landing dashboard: compliance alerts, risk flags, regulatory task checklist.
Email | Client | Log of emails sent to clients and date | Used | Client 360 View → Previous Emails table: date-sorted email list; clicking an email body opens a popup with the full email chain (including replies). Client Engagement Q&A: ask natural-language questions about emails and get sourced answers.
EmailInsight | Client | Extraction of email sentiment, products mentioned, summary and participants | Used | Client 360 View → Previous Emails → "View Insights" button: opens a popup/panel showing AI-generated insights per email (sentiment, key topics, action items).
EmailReply | Client | Raw customer replies to emails | Used | Email Chain Popup (inside Previous Emails): reply thread rendered below the original email body in chronological order.
MarketHighlights | Market | List of market events and title | Used | Market Highlights card on the landing dashboard: market news headlines, key economic indicators, and summary blurbs.
NextBestAction | Client | List of prioritized actions by client based on email convo | Used | Client 360 View → Next Best Actions panel: detailed action cards per client with recommended actions, pre-drafted email templates, and priority labels. Also queryable via copilot.
NextBestActionLandingPage | Client | High-level list of actions by client | Used | Next Best Actions summary card on the landing dashboard: prioritized action items with client name, action type, and urgency.
OpenOpportunities | Advisor | Opportunities listed by advisor (not client) | Used | Open Opportunities card on the landing dashboard: list of pending sales/service opportunities with client name, product, and status.
PortfolioData | Client | Full list of portfolio by client, goals, statos (on track) and summary | Used | Client 360 View → Portfolio panel: holdings table, asset allocation breakdown, portfolio performance chart. Indirectly powers landing page My Performance (AUM aggregation) and My Clients (wallet share column). Also queryable via Ask Aeon copilot.
PortfolioSimulator | Advisor | ??? | Used | Portfolio Simulator card on the landing dashboard: interactive allocation chart with sliders; shows projected returns vs current AUM.
SmartInsights | Client | Summary recommendations on what actions to take for certain type of clients | Unused
SocialListening | Market | ??? | Used | Social Listening card on the landing dashboard: trending topics with sentiment indicators (positive/negative/neutral).
Transcript | Client | Phone call transcripts with tagged call type, sentiment and products mentioned by client | Used | Client 360 View → Previous Calls table: date-sorted call list with call type, duration, products mentioned, sentiment badge; "View Insights" button per row. Client Engagement Q&A panel for natural-language queries across calls. Post-Call Dashboard (currently uses local JSON, not live API).
TranscriptInsights | Client | Processed transcripts with product types, next steps, behavioral insights etc | Used | Transcript Insights Modal: opened via "View Insights" button on each call row; shows AI-generated call summary, key topics, sentiment analysis, and action items.
TransriptSummary | Client | Summary of each transcript | Used | No dedicated UI. Indirectly reachable when the Ask Aeon copilot generates SQL that touches this table.
UpcomingClientMeetings | Client | List of upcoming appointments by client | Used | Upcoming Meetings card on the landing dashboard: today's and tomorrow's meetings listed by client name, meeting type, and time; client profile picture shown.
Table: | Description
public_AIGroupInsight | Call and client summaries and categorization of call, goals and wealth topics |  |  |  | Questions:
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description | Is this data supposed to come from one call/interaction with a client or does it theoretically combine multiple past interactionsa nd multiple data sosurces?
Integer | Y | Y | public_AIGroupInsight.Id | Primary key identifier for public_AIGroupInsight | Can this table be generated and maintained automatically in prod?
Integer | N | Y | public_AIGroupInsight.ClientId | Identifier linking to a client in public_AIGroupInsight
JSON array (text) | N | N | public_AIGroupInsight.CommonProducts | Common Products field in public_AIGroupInsight
Text | N | N | public_AIGroupInsight.AttritionSignals | Attrition Signals field in public_AIGroupInsight
Text | N | N | public_AIGroupInsight.OverdueAdvisorTasks | Overdue Advisor Tasks field in public_AIGroupInsight
JSON array (text) | N | N | public_AIGroupInsight.DiscussionTopics | Discussion Topics field in public_AIGroupInsight
Text | N | N | public_AIGroupInsight.ClientSummary | Narrative summary text captured for public_AIGroupInsight
Text | N | N | public_AIGroupInsight.SummaryClient | Narrative summary text captured for public_AIGroupInsight
Text | N | N | public_AIGroupInsight.SupportingTopics | Supporting Topics field in public_AIGroupInsight
JSON object (text) | N | N | public_AIGroupInsight.SmartInsights | Smart Insights field in public_AIGroupInsight
JSON object (text) | N | N | public_AIGroupInsight.CommunicationTimeline | Communication Timeline field in public_AIGroupInsight
Text | N | N | public_AIGroupInsight.OverallCallSumarries | Overall Call Sumarries field in public_AIGroupInsight
Table: | Description
public_AdvisorClients | Client-advisor mapping, client type and total asset amount
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description
Integer | Y | Y | public_AdvisorClients.Id | Primary key identifier for public_AdvisorClients
Integer | N | N | public_AdvisorClients.AdvisorId | Identifier linking to an advisor in public_AdvisorClients
Integer | N | Y | public_AdvisorClients.ClientId | Identifier linking to a client in public_AdvisorClients
Text | N | N | public_AdvisorClients.ClientName | Client Name field in public_AdvisorClients
Text | N | N | public_AdvisorClients.ImageSrc | Image Src field in public_AdvisorClients
Text | N | N | public_AdvisorClients.Persona | Client/advisor segment label used in public_AdvisorClients
Text | N | N | public_AdvisorClients.Amount | Financial amount/metric stored in public_AdvisorClients
Integer | N | N | public_AdvisorClients.Date | Date associated with the public_AdvisorClients record
Table: | Description
public_AdvisorCoaching | ???
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description | Is this table used? Only two rows
Integer | Y | Y | public_AdvisorCoaching.Id | Primary key identifier for public_AdvisorCoaching
Integer | N | Y | public_AdvisorCoaching.AdvisorId | Identifier linking to an advisor in public_AdvisorCoaching
JSON array (text) | N | N | public_AdvisorCoaching.Credits | Credits field in public_AdvisorCoaching
JSON array (text) | N | N | public_AdvisorCoaching.Trainings | Trainings field in public_AdvisorCoaching
Text | N | N | public_AdvisorCoaching.Persona | Client/advisor segment label used in public_AdvisorCoaching
Table: | Description
public_AdvisorDetails | Description of advisors, # accounts etc
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description | Is this table used? Only two rows
Integer | Y | Y | public_AdvisorDetails.Id | Primary key identifier for public_AdvisorDetails
Integer | N | Y | public_AdvisorDetails.AdvisorId | Identifier linking to an advisor in public_AdvisorDetails
Text | N | N | public_AdvisorDetails.Name | Name field in public_AdvisorDetails
Text | N | N | public_AdvisorDetails.ImageSrc | Image Src field in public_AdvisorDetails
Integer | N | N | public_AdvisorDetails.NoOfAccounts | No Of Accounts field in public_AdvisorDetails
Integer | N | N | public_AdvisorDetails.NewTasks | New Tasks field in public_AdvisorDetails
Text | N | N | public_AdvisorDetails.PeerRanking | Peer Ranking field in public_AdvisorDetails
Integer | N | N | public_AdvisorDetails.OpenOpportunities | Open Opportunities field in public_AdvisorDetails
JSON array (text) | N | N | public_AdvisorDetails.AeonNudges | Aeon Nudges field in public_AdvisorDetails
Text | N | N | public_AdvisorDetails.Persona | Client/advisor segment label used in public_AdvisorDetails
Table: | Description
public_AdvisorPerformance | Description of advisor performance (revenue, growth)
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description | Is this table used? Only two rows
Integer | Y | Y | public_AdvisorPerformance.Id | Primary key identifier for public_AdvisorPerformance
Integer | N | Y | public_AdvisorPerformance.AdvisorId | Identifier linking to an advisor in public_AdvisorPerformance
Text | N | N | public_AdvisorPerformance.Persona | Client/advisor segment label used in public_AdvisorPerformance
JSON array (text) | N | N | public_AdvisorPerformance.AssetSegments | Asset Segments field in public_AdvisorPerformance
JSON array (text) | N | N | public_AdvisorPerformance.RevenueSegments | Financial amount/metric stored in public_AdvisorPerformance
JSON object (text) | N | N | public_AdvisorPerformance.Aum | Financial amount/metric stored in public_AdvisorPerformance
JSON object (text) | N | N | public_AdvisorPerformance.Revenue | Financial amount/metric stored in public_AdvisorPerformance
Table: | Description
public_chat_memory | Past queries and responses log, agents used
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description
Integer | Y | Y | public_chat_memory.id | Primary key identifier for public_chat_memory
Text | N | N | public_chat_memory.user_query | user query field in public_chat_memory
Text | N | N | public_chat_memory.agents | agents field in public_chat_memory
Text | N | N | public_chat_memory.responses | responses field in public_chat_memory
Date | N | N | public_chat_memory.created_at | created at field in public_chat_memory
Table: | Description
public_ClientDetails | Details about clients, name, goals, marital status, household, sentiment, status etc
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description
Integer | N | Y | public_ClientDetails.ClientId | Identifier linking to a client in public_ClientDetails
Integer | N | N | public_ClientDetails.AdvisorId | Identifier linking to an advisor in public_ClientDetails
Text | N | N | public_ClientDetails.Persona | Client/advisor segment label used in public_ClientDetails
Text | N | N | public_ClientDetails.Name | Name field in public_ClientDetails
Text | N | N | public_ClientDetails.ImageSrc | Image Src field in public_ClientDetails
Integer | N | N | public_ClientDetails.Age | Age field in public_ClientDetails
Text | N | N | public_ClientDetails.Location | Location field in public_ClientDetails
Text | N | N | public_ClientDetails.MaritalStatus | Marital Status field in public_ClientDetails
JSON array (text) | N | N | public_ClientDetails.FinancialGoals | Financial Goals field in public_ClientDetails
Text | N | N | public_ClientDetails.OccupationInfo | Occupation Info field in public_ClientDetails
JSON array (text) | N | N | public_ClientDetails.Interests | Interests field in public_ClientDetails
JSON array (text) | N | N | public_ClientDetails.UpcomingLifeEvents | Upcoming Life Events field in public_ClientDetails
Text | N | N | public_ClientDetails.AttritionRisk | Attrition Risk field in public_ClientDetails
Text | N | N | public_ClientDetails.ClientSentiment | Client Sentiment field in public_ClientDetails
Text | N | N | public_ClientDetails.ClientWebData | Client Web Data field in public_ClientDetails
Text | N | N | public_ClientDetails.ClientNPS | Client NPS field in public_ClientDetails
Text | N | N | public_ClientDetails.ClientTransactionActivity | Client Transaction Activity field in public_ClientDetails
Text | N | N | public_ClientDetails.Household | Household field in public_ClientDetails
Text | N | N | public_ClientDetails.InvestorType | Investor Type field in public_ClientDetails
Text | N | N | public_ClientDetails.PreferredName | Preferred Name field in public_ClientDetails
Text | N | N | public_ClientDetails.ClientTenure | Client Tenure field in public_ClientDetails
Text | N | N | public_ClientDetails.ClientLifeStyle | Client Life Style field in public_ClientDetails
Text | N | N | public_ClientDetails.TaxSensitivity | Tax Sensitivity field in public_ClientDetails
JSON object (text) | N | N | public_ClientDetails.SpouseOutsideAssetsAISummary | Narrative summary text captured for public_ClientDetails
Integer | N | N | public_ClientDetails.NextAppointment | Next Appointment field in public_ClientDetails
Table: | Description
public_CollaborationHub | Summary of which clients each advisor has
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description | How is this useful compared to AdvisorClients table?
Integer | Y | Y | public_CollaborationHub.Id | Primary key identifier for public_CollaborationHub
Integer | N | N | public_CollaborationHub.AdvisorId | Identifier linking to an advisor in public_CollaborationHub
Text | N | N | public_CollaborationHub.Name | Name field in public_CollaborationHub
Text | N | N | public_CollaborationHub.Persona | Client/advisor segment label used in public_CollaborationHub
JSON array (text) | N | N | public_CollaborationHub.Clients | Clients field in public_CollaborationHub
Table: | Description
public_ComplianceHub | List of clients and their next compliance-related recommendation
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description
Integer | Y | Y | public_ComplianceHub.Id | Primary key identifier for public_ComplianceHub
Integer | N | Y | public_ComplianceHub.ClientId | Identifier linking to a client in public_ComplianceHub
Text | N | N | public_ComplianceHub.ClientName | Client Name field in public_ComplianceHub
Text | N | N | public_ComplianceHub.ImageSrc | Image Src field in public_ComplianceHub
Text | N | N | public_ComplianceHub.Persona | Client/advisor segment label used in public_ComplianceHub
Text | N | N | public_ComplianceHub.Recommendation | Recommended action/next step in public_ComplianceHub
Table: | Description
public_Email | Log of emails sent to clients and date
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description
Integer | Y | Y | public_Email.Id | Primary key identifier for public_Email
Integer | N | N | public_Email.IdEmail | Id Email field in public_Email
Integer | N | N | public_Email.ClientId | Identifier linking to a client in public_Email
Text | N | N | public_Email.Subject | Subject field in public_Email
Text | N | N | public_Email.Body | Body field in public_Email
Date | N | N | public_Email.Date | Date associated with the public_Email record
Table: | Description
public_EmailInsight | Extraction of email sentiment, products mentioned, summary and participants
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description
Integer | Y | Y | public_EmailInsight.Id | Primary key identifier for public_EmailInsight
Integer | N | N | public_EmailInsight.ClientId | Identifier linking to a client in public_EmailInsight
Integer | N | N | public_EmailInsight.IdEmail | Id Email field in public_EmailInsight
Text | N | N | public_EmailInsight.Sentiment | Sentiment field in public_EmailInsight
JSON array (text) | N | N | public_EmailInsight.ProductsMentioned | Products Mentioned field in public_EmailInsight
Text | N | N | public_EmailInsight.Summary | Narrative summary text captured for public_EmailInsight
JSON array (text) | N | N | public_EmailInsight.Participants | Participants field in public_EmailInsight
Table: | Description
public_EmailReply | Raw customer replies to emails
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description
Integer | Y | Y | public_EmailReply.Id | Primary key identifier for public_EmailReply
Integer | N | N | public_EmailReply.ClientId | Identifier linking to a client in public_EmailReply
Integer | N | N | public_EmailReply.IdEmail | Id Email field in public_EmailReply
Text | N | N | public_EmailReply.Subject | Subject field in public_EmailReply
Text | N | N | public_EmailReply.Body | Body field in public_EmailReply
Integer | N | N | public_EmailReply.Date | Date associated with the public_EmailReply record
Table: | Description
public_MarketHighlights | List of market events and title
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description | No date and not many details here. Is this something we need to expand on?
Integer | Y | Y | public_MarketHighlights.Id | Primary key identifier for public_MarketHighlights
Text | N | N | public_MarketHighlights.Title | Title field in public_MarketHighlights
Text | N | N | public_MarketHighlights.Description | Description field in public_MarketHighlights
Table: | Description
public_NexstBestAction | List of prioritized actions by client based on email convo
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description | Why is the email body here? Should that not live in the email table?
Integer | Y | Y | public_NextBestAction.Id | Primary key identifier for public_NextBestAction
Integer | N | N | public_NextBestAction.ClientId | Identifier linking to a client in public_NextBestAction
Text | N | N | public_NextBestAction.Title | Title field in public_NextBestAction
Text | N | N | public_NextBestAction.Text | Text field in public_NextBestAction
Text | N | N | public_NextBestAction.EmailRecipient | Email Recipient field in public_NextBestAction
Text | N | N | public_NextBestAction.EmailSubject | Email Subject field in public_NextBestAction
Text | N | N | public_NextBestAction.EmailBody | Email Body field in public_NextBestAction
Text | N | N | public_NextBestAction.Trigger | Trigger field in public_NextBestAction
Text | N | N | public_NextBestAction.Priority | Priority field in public_NextBestAction
Text | N | N | public_NextBestAction.AdvisorAction | Advisor Action field in public_NextBestAction
Table: | Description
public_NextBestActionLandingPage | High-level list of actions by client
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description | Why is client name, image and persona here?
Integer | Y | Y | public_NextBestActionLandingPag.Id | Primary key identifier for public_NextBestActionLandingPag | Not the same number of IDs as NextBestAction table. Should these not be 1-1?
Integer | N | Y | public_NextBestActionLandingPag.ClientId | Identifier linking to a client in public_NextBestActionLandingPag
Text | N | N | public_NextBestActionLandingPag.ClientName | Client Name field in public_NextBestActionLandingPag
Text | N | N | public_NextBestActionLandingPag.ImageSrc | Image Src field in public_NextBestActionLandingPag
Text | N | N | public_NextBestActionLandingPag.Persona | Client/advisor segment label used in public_NextBestActionLandingPag
Text | N | N | public_NextBestActionLandingPag.Recommendation | Recommended action/next step in public_NextBestActionLandingPag
Text | N | N | public_NextBestActionLandingPag.Action | Action field in public_NextBestActionLandingPag
Table: | Description
public_OpenOpportunities | Opportunities listed by advisor (not client)
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description
Integer | Y | Y | public_OpenOpportunities.Id | Primary key identifier for public_OpenOpportunities
Integer | N | N | public_OpenOpportunities.AdvisorId | Identifier linking to an advisor in public_OpenOpportunities
Text | N | N | public_OpenOpportunities.Name | Name field in public_OpenOpportunities
Boolean | N | N | public_OpenOpportunities.Checked | Checked field in public_OpenOpportunities
Text | N | N | public_OpenOpportunities.Action | Action field in public_OpenOpportunities
Text | N | N | public_OpenOpportunities.Persona | Client/advisor segment label used in public_OpenOpportunities
Table: | Description
public_PortfolioData | Full list of portfolio by client, goals, statos (on track) and summary
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description
Integer | Y | Y | public_PortfolioData.Id | Primary key identifier for public_PortfolioData
Integer | N | Y | public_PortfolioData.ClientId | Identifier linking to a client in public_PortfolioData
Decimal | N | N | public_PortfolioData.TotalValue | Total Value field in public_PortfolioData
Integer | N | N | public_PortfolioData.AnnualIncome | Annual Income field in public_PortfolioData
Text | N | N | public_PortfolioData.Focus | Focus field in public_PortfolioData
Text | N | N | public_PortfolioData.RiskTolerance | Risk Tolerance field in public_PortfolioData
Text | N | N | public_PortfolioData.Breakdown | Breakdown field in public_PortfolioData
Text | N | N | public_PortfolioData.RiskCategory | Risk Category field in public_PortfolioData
Text | N | N | public_PortfolioData.PotentialRisk | Potential Risk field in public_PortfolioData
Integer | N | N | public_PortfolioData.WalletShare | Wallet Share field in public_PortfolioData
Text | N | N | public_PortfolioData.TotalOutsideAssetsValue | Total Outside Assets Value field in public_PortfolioData
JSON array (text) | N | N | public_PortfolioData.OutsideAssetsHoldings | Outside Assets Holdings field in public_PortfolioData
Text | N | N | public_PortfolioData.Goals | Goals field in public_PortfolioData
Text | N | N | public_PortfolioData.GoalStatus | Goal Status field in public_PortfolioData
Text | N | N | public_PortfolioData.PortfolioAISummary | Narrative summary text captured for public_PortfolioData
Table: | Description
public_PortfolioSimulator | ??
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description | Only two rows, is this used?
Integer | Y | Y | public_PortfolioSimulator.Id | Primary key identifier for public_PortfolioSimulator
Integer | N | N | public_PortfolioSimulator.AdvisorId | Identifier linking to an advisor in public_PortfolioSimulator
JSON array (text) | N | N | public_PortfolioSimulator.DataSets | Data Sets field in public_PortfolioSimulator
Text | N | N | public_PortfolioSimulator.Persona | Client/advisor segment label used in public_PortfolioSimulator
JSON array (text) | N | N | public_PortfolioSimulator.Labels | Labels field in public_PortfolioSimulator
Table: | Description
public_SmartInsights | Summary recommendations on what actions to take for certain type of clients
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description | Why are multiple clients references in the Items section despite there being a unique ClientID?
Integer | Y | Y | public_SmartInsights.Id | Primary key identifier for public_SmartInsights
Integer | N | Y | public_SmartInsights.ClientId | Identifier linking to a client in public_SmartInsights
Text | N | N | public_SmartInsights.Title | Title field in public_SmartInsights
JSON array (text) | N | N | public_SmartInsights.Items | Items field in public_SmartInsights
Date | N | N | public_SmartInsights.CreatedAt | Created At field in public_SmartInsights
Date | N | N | public_SmartInsights.UpdatedAt | Updated At field in public_SmartInsights
Table: | Description
public_SocialListening | ???
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description
Integer | Y | Y | public_SocialListening.Id | Primary key identifier for public_SocialListening
Text | N | N | public_SocialListening.Topic | Topic field in public_SocialListening
Integer | N | N | public_SocialListening.Frequency | Frequency field in public_SocialListening
Integer | N | N | public_SocialListening.Positive | Positive field in public_SocialListening
Integer | N | N | public_SocialListening.Negative | Negative field in public_SocialListening
Integer | N | N | public_SocialListening.Neutral | Neutral field in public_SocialListening
Text | N | N | public_SocialListening.Persona | Client/advisor segment label used in public_SocialListening
Table: | Description
public_Transcript | Phone call transcripts with tagged call type, sentiment and products mentioned by client
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description | Why is transcript ID not unique for each row?
Integer | Y | Y | public_Transcript.Id | Primary key identifier for public_Transcript
Integer | N | N | public_Transcript.TranscriptId | Identifier for related entity (TranscriptId) in public_Transcript
Integer | N | N | public_Transcript.ClientId | Identifier linking to a client in public_Transcript
Integer | N | N | public_Transcript.Date | Date associated with the public_Transcript record
Text | N | N | public_Transcript.CallType | Call Type field in public_Transcript
JSON array (text) | N | N | public_Transcript.ProductsMentioned | Products Mentioned field in public_Transcript
Text | N | N | public_Transcript.Duration | Duration field in public_Transcript
Text | N | N | public_Transcript.Transcript | Transcript field in public_Transcript
Text | N | N | public_Transcript.Sentiment | Sentiment field in public_Transcript
Table: | Description
public_TranscriptInsights | Processed transcripts with product types, next steps, behavioral insights etc
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description
Integer | Y | Y | public_TranscriptInsights.Id | Primary key identifier for public_TranscriptInsights
Integer | N | N | public_TranscriptInsights.ClientId | Identifier linking to a client in public_TranscriptInsights
Integer | N | N | public_TranscriptInsights.TranscriptId | Identifier for related entity (TranscriptId) in public_TranscriptInsights
Text | N | N | public_TranscriptInsights.Sentiment | Sentiment field in public_TranscriptInsights
Text | N | N | public_TranscriptInsights.Type | Type field in public_TranscriptInsights
JSON array (text) | N | N | public_TranscriptInsights.ProductsMentioned | Products Mentioned field in public_TranscriptInsights
Text | N | N | public_TranscriptInsights.Summary | Narrative summary text captured for public_TranscriptInsights
Text | N | N | public_TranscriptInsights.NextSteps | Next Steps field in public_TranscriptInsights
JSON array (text) | N | N | public_TranscriptInsights.FinancialConcerns | Financial Concerns field in public_TranscriptInsights
JSON array (text) | N | N | public_TranscriptInsights.RecentEvents | Recent Events field in public_TranscriptInsights
JSON array (text) | N | N | public_TranscriptInsights.BehaviouralInsights | Behavioural Insights field in public_TranscriptInsights
Table: | Description
public_TranscriptSummary | Summary of each transcript
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description | Why is there a separate summary table when a summary exists in the TranscriptInsights table?
Integer | Y | Y | public_TranscriptSummary.Id | Primary key identifier for public_TranscriptSummary
Integer | N | N | public_TranscriptSummary.ClientId | Identifier linking to a client in public_TranscriptSummary
Integer | N | N | public_TranscriptSummary.TranscriptId | Identifier for related entity (TranscriptId) in public_TranscriptSummary
Text | N | N | public_TranscriptSummary.Summary | Narrative summary text captured for public_TranscriptSummary
Table: | Description
public_UpcomingClientMeetings | List of upcoming appointments by client
Data type | Primary_key (Y/N) | Unique_identifier (Y/N) | Column_name | Column_description | Why is client name and persona etc in this table as well?
Integer | Y | Y | public_UpcomingClientMeetings.Id | Primary key identifier for public_UpcomingClientMeetings
Integer | N | Y | public_UpcomingClientMeetings.ClientId | Identifier linking to a client in public_UpcomingClientMeetings
Text | N | N | public_UpcomingClientMeetings.ClientName | Client Name field in public_UpcomingClientMeetings
Text | N | N | public_UpcomingClientMeetings.ImageSrc | Image Src field in public_UpcomingClientMeetings
Text | N | N | public_UpcomingClientMeetings.Persona | Client/advisor segment label used in public_UpcomingClientMeetings
Text | N | N | public_UpcomingClientMeetings.MeetingType | Meeting Type field in public_UpcomingClientMeetings
Text | N | N | public_UpcomingClientMeetings.MeetingDay | Meeting Day field in public_UpcomingClientMeetings
Text | N | N | public_UpcomingClientMeetings.MeetingTime | Meeting Time field in public_UpcomingClientMeetings

## AI Features (OLD)
Feature # | Feature Name | Category | Description | Component / File | AI Mechanism | User Interaction | Primary Agent (Pure Agentic) | Supporting Agents | Utilities / Infra | Effort estimation
1 | Conversational Chat | Chat & Conversational AI | Core chat interface where advisors ask questions and get context-aware responses about clients, opportunities, and planning. Maintains conversation history for multi-turn dialogue. | src/components/ChatLayer.tsx | Supabase edge function 'aeon-chat' → Gemini 2.5 Flash LLM; streaming SSE responses with conversation history | Types message, clicks send, receives streamed response | Meta-Agent | Narrative Agent | Memory, Streaming
2 | Quick Action Prompts | Chat & Conversational AI | Pre-defined action buttons that trigger common advisor workflows (summarize client, find urgent opportunities, prep meeting, show top leads). | src/components/ChatLayer.tsx | Preset prompts routed to aeon-chat edge function | Clicks quick action button (e.g. 'Summarize Johnson household') | Meta-Agent | Narrative Agent | UI Triggers
3 | Opportunity Extraction & Highlighting | Chat & Conversational AI | Parses special tokens [OPPORTUNITY:id:name:title:priority] from LLM responses to display linked opportunity cards in chat. | src/components/ChatLayer.tsx | Regex parser on LLM response text; token-based structured data extraction | Automatic — advisor sees highlighted opportunity cards in response | Narrative Agent | Opportunity Agent | Token Parser
4 | Meeting Prep Context Activation | Chat & Conversational AI | Detects meeting-related keywords (e.g. 'prep 2pm meeting' + client name) and injects rich contextual data into LLM prompts. | src/components/ChatLayer.tsx | Heuristic keyword/intent matching + context injection into system prompt | Types meeting-related question in chat | Meta-Agent | Meeting Context Agent | Context Injection
5 | Context Assistant Panel | Chat & Conversational AI | Side panel AI assistant for quick client analysis, summarization, and opportunity discovery. | src/components/ContextAssistant.tsx | aeon-chat Supabase function (same LLM backend as ChatLayer) | Types in side panel textarea, clicks send | Narrative Agent | Meta-Agent | Context Injection | S
6 | Client Insights Ticker | Chat & Conversational AI | Auto-scrolling feed of AI-surfaced client concerns. Clicking an insight sends a prompt to main chat. | src/components/ClientInsightsTicker.tsx | Pre-curated insight library; click sends prompt to LLM chat | Auto-updates on dashboard; advisor clicks an insight card | Narrative Agent | Meta-Agent | Curated Content | S
7 | Day-Ahead Agenda Generation | Chat & Conversational AI | AI generates a time-blocked daily schedule with client meetings, tasks, and breaks. Supports Word export. | src/components/DayAheadAgendaDialog.tsx | aeon-chat function with custom prompt requesting structured agenda format | Clicks 'Generate Agenda' or dialog opens automatically | Meta-Agent | Narrative Agent | Memory, Export
8 | Financial Planning Chat | Financial Planning AI | Streaming conversational interface for building and refining financial plans. Supports plan/whatif/draft modes. | src/components/planning/PlanningChat.tsx | Supabase edge function 'financial-planning' → Gemini 2.5 Flash; streaming SSE; CFP-aligned system prompt | Types planning questions, receives streamed response | Financial Agent | Meta-Agent | Streaming
9 | Plan Item Extraction | Financial Planning AI | Parses [PLAN_ITEM:category:title:priority:timeframe] tokens from LLM responses to create actionable plan item cards with status tracking. | src/components/planning/PlanningChat.tsx | Regex parser on streamed response text; tokenized data extraction | Automatic during chat — advisor sees parsed plan items | Narrative Agent | Financial Agent | Token Parser
10 | Summary Card Extraction | Financial Planning AI | Parses [CARD:type:title:value:subtitle:trend] tokens to create metric cards (e.g. 'Monthly Cash Flow: $5,000'). | src/components/planning/PlanningChat.tsx | Regex token parser + card rendering component | Automatic in chat response | Narrative Agent | Financial Agent | Token Parser
11 | Guided Step-by-Step Planning | Financial Planning AI | Structured AI-assisted workflow that breaks complex planning topics into discrete steps with actions, questions, and insights. | src/components/planning/GuidedPlanner.tsx | Preset step flows + dynamic LLM generation via financial-planning function; special tags: [QUESTION], [ACTION], [EXECUTE], [CLIENT_POINT], [INSIGHT] | Selects a topic, advances through steps, makes choices | Guided Planning Agent | Meta-Agent | Memory
12 | Preset Planning Topics | Financial Planning AI | Pre-built structured workflows for common planning scenarios (cash management, tax optimization, student loans, estate, condo purchase, etc.). | src/components/planning/presetSteps.ts | Curated step JSON structures stored in source code | Clicks topic button to start guided flow | Guided Planning Agent | Financial Agent | Curated Steps
13 | AI-Generated Plan Insights | Financial Planning AI | Strategic insights embedded in plan action items (e.g. 'Deploying ~$400K at 7% over 22 years could grow to ~$1.7M vs. cash at 4.5%'). | src/components/planning/PlanDraftEditor.tsx | Injected into action items via financial-planning LLM function | Displays as highlighted callouts in plan phases | Financial Agent | Narrative Agent | Context Injection
14 | What-If Scenario Modeling | Financial Planning AI | Interactive scenario analysis with sliders (retirement age, return rate, inflation, savings) and life event toggles (car, baby, sabbatical). Shows wealth projections. | src/components/planning/WhatIfDashboard.tsx | Parameter-based wealth projection formulas + life event impact calculations (computational, not LLM) | Adjusts sliders, toggles life events, views charts in real time | Scenario Agent | Financial Agent | Deterministic Compute
15 | Scenario Comparison Output | Financial Planning AI | LLM formats scenario results using [SCENARIO:name:metric:baseValue:newValue:impact] tokens for before/after comparisons. | src/components/planning/PlanningChat.tsx | Custom token output format from financial-planning LLM in whatif mode | Automatic in whatif mode chat responses | Narrative Agent | Scenario Agent | Token Parser
16 | Client Nudges / AI Recommendations | Financial Planning AI | Pre-generated AI suggestions for client conversations — categorized as suggestions, questions, or discussion prompts. | src/components/planning/ClientNudgesSection.tsx | Pre-curated nudge library (not real-time LLM); advisors can edit before sending | Reviews, edits, and sends nudge to client | Narrative Agent | Meta-Agent | Curated Library
17 | Recommended Actions | Financial Planning AI | AI suggests high-impact action items for clients (review plan, prepare analysis, schedule meeting). | src/components/opportunity/RecommendedActions.tsx | Heuristic action generation based on opportunity type + manual curation | Clicks action to trigger workflow | Opportunity Agent | Meta-Agent | Action Surfacing
18 | Mode-Specific Planning Behavior | Financial Planning AI | LLM adjusts tone and output format based on active planning mode: plan (comprehensive), whatif (scenario), draft (refinement), guided (step-by-step). | src/components/planning/PlanningChat.tsx, supabase/functions/financial-planning/index.ts | Mode parameter passed to function; system prompt modified dynamically | System automatically detects mode from UI context | Meta-Agent | Financial Agent | Prompt Shaping
19 | Client-Specific Financial Profiles | Financial Planning AI | Deep contextual injection of client financial data into LLM system prompt (cash positions, surplus, tax brackets, goals). | supabase/functions/financial-planning/index.ts | Client profile stored in edge function; injected into system prompt before LLM call | Automatic for authenticated sessions with clientId | Meta-Agent | Financial Agent | Context Injection
20 | Opportunity Intelligence | Opportunity Detection & Analysis | Priority-ranked opportunity database (cash drag, RSU concentration, retirement gaps) surfaced in chat and dashboard cards. | supabase/functions/aeon-chat/index.ts, src/pages/Index.tsx | Pre-curated opportunity database + LLM context injection; [OPPORTUNITY:...] token parsing | Automatic display in dashboard; advisor clicks for details | Opportunity Agent | Narrative Agent | Token Parser
21 | Opportunity Signals Analysis | Opportunity Detection & Analysis | Displays key performance signals for each opportunity (e.g. 'Idle Cash: $650,000', 'Foregone Growth: $45.5K/yr'). | src/components/opportunity/OpportunityOverview.tsx | Computed metrics from client financial profile data | Displays in opportunity detail view | Opportunity Agent | Narrative Agent | Metrics Engine
22 | Prospect Value Estimation | Opportunity Detection & Analysis | Estimates prospect revenue: annual recurring revenue (AUM × 1%), 5-year growth potential, win probability (78%), retention likelihood (92%). | src/components/opportunity/ProspectValue.tsx | Formula-based calculation (AUM × fee rate, growth multiplier) + curated insight library | Displays on prospect card with 'Claim Lead' / 'Assign Lead' buttons | Prospecting Agent | Narrative Agent | Value Calculator
23 | Prospect Match Scoring | Opportunity Detection & Analysis | Rates prospects with match scores (82–94/100) and provides contextual match reasons. | src/pages/Prospecting.tsx | Pre-calculated scores in mock data; formula-based matching on search | Searches for prospects, sees ranked results | Prospecting Agent | Meta-Agent | Scoring Engine
24 | External Research Topics | Opportunity Detection & Analysis | Curated contextual research insights relevant to specific opportunities (collapsible cards). | src/components/opportunity/ExternalResearch.tsx | Static content library (curated, not LLM-generated per response) | Clicks topic to expand research summary | Opportunity Agent | Narrative Agent | Curated Research
25 | Client Needs Detection | Opportunity Detection & Analysis | Heuristic detection of clients needing attention (spending changes, goal drift, portfolio volatility, tax-loss opportunities). | src/pages/Index.tsx | Curated client attention data + keyword matching rules | Displays in 'Needs Your Attention' section on dashboard | Opportunity Agent | Narrative Agent | Heuristics
26 | Speech Recognition (STT) | Voice / Speech AI | Browser-native Web Speech API; converts spoken words to text for chat input with interim transcription. | src/hooks/useSpeechRecognition.ts | Web Speech API (SpeechRecognition / webkitSpeechRecognition); en-US | Clicks microphone button, speaks, transcript appears in chat input | UI | Meta-Agent | Web Speech API
27 | Speech Synthesis (TTS) | Voice / Speech AI | Browser-native Web Speech API; reads LLM response text aloud. Strips markdown for cleaner speech. | src/hooks/useSpeechSynthesis.ts | Web Speech API (SpeechSynthesis); 1.0x rate, 1.0x pitch | Clicks speaker icon on message to hear response read aloud | UI | Meta-Agent | Web Speech API
28 | Meeting Prep Briefing | Meeting Prep & Intelligence | Comprehensive AI-curated meeting briefing: client profile, goals, risk tolerance, portfolio, previous interactions, discussion topics, life events, attrition risk. | src/components/MeetingPrepDialog.tsx | Curated data assembly + client profile injection (structured intelligent assembly) | Triggered by meeting prep request in chat or quick action button | Meeting Context Agent | Narrative Agent | Context Assembly
29 | Meeting Prep Trigger in Chat | Meeting Prep & Intelligence | Detects 'prepare for meeting' + client name in chat input; auto-shows meeting prep with injected client context. | src/components/ChatLayer.tsx | Heuristic keyword + intent matching (regex for 'meeting' + client identifier) | Types 'prep my 2pm meeting' or similar in chat | Meta-Agent | Meeting Context Agent | Intent Detection
30 | Prospect Search & Matching | Prospecting AI | AI-powered prospect database search. Natural language queries return ranked prospects with match scores. | src/pages/Prospecting.tsx | Keyword matching + filtering on mock prospect database; simulates AI ranking | Types search query (e.g. 'Tech executives with RSU concentration'), sees ranked results | Prospecting Agent | Meta-Agent | Search Index
31 | Prospect Outreach Generation | Prospecting AI | Draft personalized outreach message based on prospect profile for lead claiming/assignment. | src/pages/Prospecting.tsx | Template-based message generation + prospect data injection (heuristic) | Clicks 'Claim Lead', optionally edits generated message | Prospecting Agent | Narrative Agent | Templates
32 | Prospect Stratification | Prospecting AI | Organizes prospects by value tier (high/medium/low) based on estimated income, net worth, and life events. | src/pages/Prospecting.tsx | Pre-calculated stratification in prospect data + match reason library | Displays in prospect list with color-coded cards | Prospecting Agent | Meta-Agent | Scoring
33 | Step-Type Variations | Planning Workflow & Guidance | Guided steps with multiple types: question, action, execute, insight, client-discussion, ai-response. Each renders differently. | src/components/planning/GuidedPlanner.tsx | Step object type system + conditional rendering; LLM generates appropriate tags | Progresses through multi-step workflow | Guided Planning Agent | Narrative Agent | Token Parser
34 | Dynamic Step Generation | Planning Workflow & Guidance | For unknown planning topics, LLM dynamically generates step sequence with action-oriented constraints. | src/components/planning/GuidedPlanner.tsx | financial-planning edge function with mode: 'guided' + special system prompt | Topic not in presets → LLM generates custom steps | Guided Planning Agent | Meta-Agent | Prompt Shaping
35 | Question with Options | Planning Workflow & Guidance | Step type showing a question with 2–3 specific answer choices. Selection advances workflow. | src/components/planning/GuidedPlanner.tsx | Preset JSON or LLM-generated [QUESTION:text:Option1¦Option2¦Option3] format | Selects an option; flow advances | Guided Planning Agent | Meta-Agent | UI Controls
36 | Free-Text Response to Questions | Planning Workflow & Guidance | Advisor provides custom text to planning questions. LLM generates a brief follow-up analysis (2–3 sentences). | src/components/planning/GuidedPlanner.tsx | LLM called via financial-planning function after custom input; generates inline ai-response step | Types custom response, AI provides analysis | Guided Planning Agent | Narrative Agent | LLM Follow-up
37 | Advisor Action Items | Planning Workflow & Guidance | Step type showing an action the advisor should complete before moving forward. | src/components/planning/GuidedPlanner.tsx | Preset step definition or LLM-generated [ACTION:...] tag | Reviews action, marks complete, advances | Meta-Agent | Guided Planning Agent | Memory
38 | Execute Steps | Planning Workflow & Guidance | Concrete, immediately executable actions (e.g. 'Set up automatic monthly transfers'). | src/components/planning/GuidedPlanner.tsx | Preset step or LLM-generated [EXECUTE:title:description] tag | Triggers execution or marks complete | Meta-Agent | Guided Planning Agent | Execution Hooks
39 | Client Discussion Points | Planning Workflow & Guidance | Steps indicating topics to discuss with client in next meeting. | src/components/planning/GuidedPlanner.tsx | Preset step or LLM-generated [CLIENT_POINT:...] tag | Notes point for upcoming client conversation | Narrative Agent | Guided Planning Agent | Memory
40 | Pre-Written Smart Responses | Client Intelligence | aeon-chat detects client context and returns pre-curated, comprehensive responses from clientInsightsResponses database. | supabase/functions/aeon-chat/index.ts | Pre-written DB + keyword detection via detectClientContext() function | Asks about a known client scenario; pre-written response returned | Client Intelligence Agent | Narrative Agent | Curated Responses
41 | Client Context Prioritization | Client Intelligence | For each chat message, system detects which client is being discussed and prioritizes relevant profile data. | supabase/functions/aeon-chat/index.ts | Keyword/regex matching against client names and chat patterns | Automatic during chat | Meta-Agent | Client Intelligence Agent | Context Prioritization
42 | Silent Client Detection | Client Intelligence | Dashboard identifies clients with no recent contact and marks them as 'silent' — opportunity to re-engage. | src/pages/Index.tsx | Heuristic: last interaction date vs current date; displayed as dashboard cards | Displays on dashboard as attention items | Opportunity Agent | Client Intelligence Agent | Temporal Heuristics
43 | LLM Provider: Gemini 2.5 Flash | System Architecture | Primary LLM for all generative AI tasks, accessed via Lovable AI Gateway. | supabase/functions/aeon-chat/index.ts, supabase/functions/financial-planning/index.ts | Google Gemini 2.5 Flash model via https://ai.gateway.lovable.dev API | Transparent to user; backend service | Runtime | Meta-Agent | LLM Router
44 | Fallback LLM Provider | System Architecture | If Gemini unavailable, system falls back to openai/gpt-5-mini. | supabase/functions/financial-planning/index.ts | Model array: [Gemini, GPT-5] with sequential retry logic | Automatic failover — transparent to user | Runtime | Meta-Agent | Failover Logic
45 | Streaming SSE Responses | System Architecture | Chat and planning responses stream in real-time using Server-Sent Events for responsive UX. | src/components/planning/PlanningChat.tsx | Fetch API with ReadableStream.getReader(); SSE protocol with [DONE] terminator | Real-time chat message updates (typing effect) | Runtime | UI | SSE
46 | Token-Based Structured Output | System Architecture | LLM outputs special tokens ([PLAN_ITEM:...], [OPPORTUNITY:...], [CARD:...]) that frontend regex parsers extract into structured UI components. | Multiple frontend + edge function files | Tokens injected into system prompts; frontend regex parsing | Automatic parsing of LLM responses into cards/items | Narrative Agent | All Domain Agents | Token Parser
47 | Dynamic System Prompt Customization | System Architecture | System prompts dynamically modified based on client profile, planning mode, conversation mode, and user role. | supabase/functions/aeon-chat/index.ts, supabase/functions/financial-planning/index.ts | String interpolation of client/mode data into system prompt template | Backend service logic — transparent to user | Meta-Agent | All Domain Agents | Prompt Builder

## Terminoloy
Term | Description
RMD | Required Minimum Distribution. Need to be done before dec 31 every year as of the year you turn 73 for retirements accounts
529 plan | A tax-advantaged savings account designed to help pay for education expenses. unds can be used for tuition, books, supplies, computers, and room/board at accredited colleges, universities, and vocational schools. They can also pay up to
Concentrated low-basis position | A high-risk scenario where a significant portion of an investor’s portfolio (typically 10%-20% or more) is held in a single stock, which has a very low cost basis (the original purchase price) compared to its current market value. This creates a tax dilemma: diversification requires selling the stock, which triggers a large capital gains tax liability
Family-office service model | A comprehensive wealth management structure tailored for Ultra-High-Net-Worth (UHNW) families, providing fully integrated financial and personal services. Unlike traditional financial advisory, this model often acts as a private company dedicated to managing total family assets, including investments, tax planning, estate administration, philanthropy, and lifestyle concierge services (e.g., travel, security)
Roth conversion analysis | A strategic evaluation—often called a Roth conversion feasibility study or tax optimization analysis—used to determine if moving funds from a traditional, tax-deferred IRA/401(k) to a Roth IRA is financially beneficial by paying taxes now for tax-free future withdrawals. It is needed when seeking to minimize long-term tax burdens, specifically when expecting higher future tax rates, during low-income years (e.g., retirement gaps or job loss), or when aiming to avoid required minimum distributions (RMDs)
Vesting schedule | A vesting schedule is a timeline that dictates when an employee gains full ownership of employer-provided assets, such as stock options, restricted stock units (RSUs), or retirement matching contributions. It acts as a retention tool, incentivizing employees to remain with a company to fully acquire these benefits.
Buy-sell funding | "Buy-sell" funding (or buy-sell agreement funding) is the mechanism used to finance the purchase of a departing or deceased business owner's shares by surviving owners or the entity itself. It provides liquidity to ensure business continuity, often funded via life insurance, cash reserves, or loans, to avoid financial strain during sudden ownership changes.
IPS | An Investment Policy Statement (IPS) in wealth management is a formal, written document created between an investor (or institution) and their financial advisor or portfolio manager. It serves as a comprehensive roadmap that outlines investment goals, objectives, risk tolerance, and constraints, guiding all future investment decisions.